## Question Pool
# | Question Type | Source Reference | Question | Choice A | Choice B | Choice C | Choice D | Correct Answer | Notes
1 | Multiple Choice | Slide 8–9 + Policy §5 | Which tool is the center-recommended repository used for recording, controlling, and monitoring major work scope and process changes in IBM Consulting, FNC Philippines? | QMX | MDC Percolator | Digital Controls Center (monday.com) | Cobee Lite | B – MDC Percolator | Percolator hosts separate dashboards per tower for accounts to log, monitor, and store process changes.
2 | Multiple Choice | Slide 12–13 + Policy §8 | What does the acronym "PCR" stand for in the Change Management process? | Project Control Review | Process Change Request | Process Compliance Reform | Pre-Creation Record | B – Process Change Request | A PCR is a formal document signed by both IBM and the client containing all details about a process change.
3 | True or False | Slide 10–11 + Policy §3 | True or False: Work scope and process changes can only be initiated or requested by the client. | True | False |  |  | False | Changes may be raised by either IBM or the Client.
4 | Multiple Choice | Slide 6–7, 14–15 + Policy §3.1, §3.2 | Which of the following is considered a Major Change that is required to be logged in the MDC Percolator? | Updating a hyperlink or correcting text in a Desktop Procedure (DTP) | Fulfilling an ad-hoc, one-time non-recurring reporting request | Process automation / process re-engineering resulting from continuous improvement | Attaching a refreshed presentation template to an email | C – Process automation / process re-engineering resulting from continuous improvement | Changes to existing contract, process improvements (automation), and Work at Risk are major changes.
5 | Multiple Choice | Slide 5 + Policy §4 | According to the Change Management Policy, which of the following is a key risk of implementing work scope changes without proper documentation and approval? | IBM takes the risk of not being paid for work performed | No protection of our intellectual property and no limitation on our liabilities | Potential mismatch of IBM and customer expectations leading to disputes and low customer satisfaction | All of the above | D – All of the above | All listed items are documented risks avoided by adhering to change management requirements.
6 | True or False | Slide 16–17 + Policy §3.1, §5.1 | True or False: A process change can be implemented without a signed PCR as long as it has documented approval from the PE/DPE and is logged under Work at Risk. | True | False |  |  | True | Work can be executed prior to signed PCR if documented PE/DPE approval is secured and logged under Work at Risk.
7 | Multiple Choice | Slide 6 + Policy §3.1 | Which of the following scenarios is an example of "Work at Risk"? | Changing a hyperlink in a team training deck | Hiring employees and commencing onboarding before an approved contract or signed PCR is in place | Generating an annual snapshot report from the MDC Percolator | Updating the QMS Chatbot with new FAQ responses | B – Hiring employees and commencing onboarding before an approved contract or signed PCR is in place | Hiring without approved contract, KT travel without contract, and execution with baseline impact are Work at Risk examples.
8 | Fill in the Blank | Slide 39 + Policy §1.2, §7.2 | The Key Control Objective specifically governing Delivery Work Scope and Process Changes is KCO __________. |  |  |  |  | 716 | Accepted variations: 716, KCO 716, KCO716
9 | Multiple Choice | Policy §6 (Table 5) | Under the Change Management Policy, who is primarily responsible for logging change requests into the MDC Percolator tool and routing them for approval? | Client Services Manager / Operations Manager | GEO DPL / Cluster Leader | Process Owner / Delivery Manager / Team Lead / Operations Lead | Business Controls Focal | C – Process Owner / Delivery Manager / Team Lead / Operations Lead | Process Owner/Delivery Mgr/Team Lead/Ops Lead logs change requests and routes them for approval.
10 | True or False | Slide 7 + Policy §3.2 | True or False: Minor changes, such as correcting typographical errors in a DTP or handling one-time ad-hoc requests, must be logged and approved in the MDC Percolator tool. | True | False |  |  | False | Minor changes (simple flow/hyperlinks/DTP text edits and one-time ad hoc requests) are not required to be logged in Percolator.
11 | Multiple Choice | Slide 35–36 + Policy §5.1 | After all required approvers have provided their approval for a fully implemented change entry in MDC Percolator, what final action must the Author take to close out the entry? | Delete the entry from the narratives section | Click "Commit/Relocate", tick "Implemented", and click "Relocate to Section" | Send a speedlink notification to IBM Legal | Submit a ticket in Cobee Lite under the obsoletion tab | B – Click "Commit/Relocate", tick "Implemented", and click "Relocate to Section" | Final close-out requires the Author to click Commit/Relocate, tick Implemented, and click Relocate to Section.
12 | Fill in the Blank | Policy §1.5 + Table 1 | The official, controlled version of the Change Management Policy and Requirements document is stored in the __________ tool. |  |  |  |  | Cobee Lite | Accepted variations: Cobee Lite, CobeeLite, Cobee
13 | Scenario (Multiple Choice) | Slide 6, 16–17, 24 + Policy §3.1, §5.1 | SCENARIO: A client requests an account team to immediately take over two additional accounting sub-processes not covered in the original Statement of Work (SOW). The formal PCR will take four weeks to be signed by the client's procurement team. How should the team handle this request compliant with policy? | Refuse the request and perform no action until the formal contract amendment is fully signed by the client. | Execute the tasks immediately upon client verbal request without logging anything since the client promised to pay later. | Obtain documented approval from the PE/DPE, log the entry under "Work at Risk" in the MDC Percolator with required approvals, and pursue the signed PCR. | Treat it as a minor ad-hoc request and log it in the team's internal Excel tracker without notifying leadership. | C – Obtain documented approval from the PE/DPE, log the entry under "Work at Risk" in the MDC Percolator with required approvals, and pursue the signed PCR. | Work outside contract can proceed ahead of signed PCR only if documented PE/DPE approval is secured and logged under Work at Risk.
14 | Scenario (Multiple Choice) | Slide 26, 39 + Policy §5.1 (Table 4), §7.2 | SCENARIO: A team lead developed a robotic process automation (RPA) bot that automates a daily transactional process. Before implementing this change in production delivery, what key prerequisites and documentation must be validated per KCO 716 and the Implementation phase? | Only an email approval from the immediate shift supervisor is required. | Validate updated Delivery Process Documentation (DTP), updated Separation of Duties (SOD), Inter-company Agreements (ICAs/SLAs), and ERO/GDPR assessments prior to implementation. | No documentation is required if the automation improves processing speed by more than 50%. | Wait until year-end audit testing before logging the automation in the MDC Percolator. | B – Validate updated Delivery Process Documentation (DTP), updated Separation of Duties (SOD), Inter-company Agreements (ICAs/SLAs), and ERO/GDPR assessments prior to implementation. | KCO 716 and Implementation phase mandate DTP updates, SOD validation, ICAs/SLAs updates, and ERO/GDPR evaluations prior to go-live.
15 | Scenario (Multiple Choice) | Slide 39 + Policy §7.2 (Attribute 716h) | SCENARIO: During the entire calendar year, an account had zero work scope or process changes executed. According to KCO 716 attribute 716h, what requirement must be satisfied at year-end? | The account is automatically marked non-compliant and receives a control deficiency. | The tester / team must enter 1 sample at year-end with no defect that demonstrates no work scope and process changes occurred. | The account lead must create a fictitious change entry in MDC Percolator to pass the audit. | The account must submit a waiver request to IBM Corporate Legal. | B – The tester / team must enter 1 sample at year-end with no defect that demonstrates no work scope and process changes occurred. | Attribute 716h specifies that if no changes were executed, 1 sample with no defect must be entered at year end to demonstrate this.